## Functional Req. Tracker
Jira Space | Master Epic # | Master Epic | Sub- Epic # | Sub-Epic | Sub-Epic Priority | Story Type (UI / Backend) | U/Story | U/Story # | Sprint No.(s) | Sprint Start Date | Sprint End Date | Requirements Gathering Status | Wireframes Status | Story Readiness Status | Grooming Status | Remarks
OdysseyONE | LINX-5943 | Order Capability | LINX-7552 | Integrated Order Creation & Validation | 1 | Backend | Data Mapping for Integrated Orders | LINX-8063 | 28, 29, 33 | 28 : 11-Feb-26 29 : 25-Feb-26 33 : 22-Apr-26 | 28 : 24-Feb-26 29 : 10-Mar-26 33 : 05-May-26 | Complete | Not Required | 2026-02-09 | 2026-02-09 | Same validations as Phase 1. Orders from the legacy TMS are already validated unlike orders from LINX
OdysseyONE | LINX-5943 | Order Capability | LINX-7552 | Integrated Order Creation & Validation | 1 | Backend | Validations for Integrated Orders - Mandatory fields | LINX-8064 |  |  |  | Complete | Yet to Start | 2026-02-09 | 2026-02-09 | Same validations as Phase 1. Orders from the legacy TMS are already validated unlike orders from LINX
OdysseyONE | LINX-5943 | Order Capability | LINX-7552 | Integrated Order Creation & Validation | 1 | Backend | Validations for Integrated Orders - Conditional fields | LINX-8066 |  |  |  | Complete | Yet to Start | 2026-02-09 | 2026-02-09 | Same validations as Phase 1. Orders from the legacy TMS are already validated unlike orders from LINX
OdysseyONE | LINX-5943 | Order Capability | LINX-7552 | Integrated Order Creation & Validation | 1 | Backend | Validations for Integrated Orders - Additional fields | LINX-8067 |  |  |  | Complete | Yet to Start | 2026-02-09 | 2026-02-09 | Same validations as Phase 1. Orders from the legacy TMS are already validated unlike orders from LINX
OdysseyONE | LINX-5943 | Order Capability | LINX-7552 | Integrated Order Creation & Validation | 1 | UI | OIF UI to fix validation errors for integrated orders | LINX-11137 |  |  |  | In Progress | Yet to Start | Yet to Start | Yet to Start
OdysseyONE | LINX-5943 | Order Capability | LINX-7552 | Integrated Order Creation & Validation | 1 | Backend | Country, Region, City and Postal Code - Validation for Integrated Orders | LINX-8068 |  |  |  | Complete | Yet to Start | 2026-02-09 | 2026-02-10 | Same validations as Phase 1. Orders from the legacy TMS are already validated unlike orders from LINX
OdysseyONE | LINX-5943 | Order Capability | LINX-7552 | Integrated Order Creation & Validation | 1 | Backend | QCA Routing Call from Order (Integrated Order) | LINX-9021 |  |  |  | Complete | Not Required | 2026-04-10 | 24-Feb-26 (Earlier story applies) | Requested on 10-Apr-26 to create separate stories for Manual & Integ Orders
OdysseyONE | LINX-5943 | Order Capability | LINX-7552 | Integrated Order Creation & Validation | 1 | Backend | QCP Rating Call from Order (Integrated Order) | LINX-9020 |  |  |  | Complete | Not Required | 2026-04-10 | 24-Feb-26 (Earlier story applies) | Requested on 10-Apr-26 to create separate stories for Manual & Integ Orders
OdysseyONE | LINX-5943 | Order Capability | LINX-7552 | Integrated Order Creation & Validation | 1 | Backend | Integrated Order - Cancelling a non-existent order - Rephrase Error Message | LINX - 10683 |  |  |  | Complete | Not Required | 2026-05-29 | N/A - Feedback from the Demo | Feedback from Demo on 28-May-26
OdysseyONE | LINX-5943 | Order Capability | LINX-7558 | Master Data Integration | 2 | Backend | Master Data for Order Creation | LINX-8062 | 28 - 30 | 28 : 11-Feb-26 29 : 25-Feb-26 30 : 11-Mar-26 | 28 : 24-Feb-26 29 : 10-Mar-26 30 : 24-Mar-26 | Complete | Not Required | 2026-02-09 | 2026-02-10 | Same validations as Phase 1. Orders from the legacy TMS are already validated unlike orders from LINX
OdysseyONE | LINX-5943 | Order Capability | LINX-7555 | Order Lifecycle Management | 3 | Backend | Order Lifecycle for Integrated Orders | LINX-6001 | 31-33 | 31 : 25-Mar-26 32 : 08-Apr-26 33 : 22-Apr-26 | 31 : 07-Apr-26 32 : 21-Apr-26 33 : 05-May-26 | Complete | Not Required | 2026-01-29 | 2-Feb-26 | Order Statuses for orders from customer ERP
OdysseyONE | LINX-5943 | Order Capability | LINX-7555 | Order Lifecycle Management | 3 | Backend | Order Lifecycle for Manual Orders | LINX-6081 |  |  |  | Complete | Not Required | 2026-01-29 | 2-Feb-26 | Order Statuses for orders from UI
OdysseyONE | LINX-5943 | Order Capability | LINX-7555 | Order Lifecycle Management | 3 | Backend | Order Lifecycle during Order Editing (Manual & Integrated Orders) | LINX-11185
OdysseyONE | LINX-5943 | Order Capability | LINX-7958 | Audit Trail | 4** | UI | Audit Trail for Manual & Integrated Orders (Single Line Item) - View Actions & Events | LINX-8091 |  |  |  | Complete | Yet to Start | 2026-02-18 | 2026-02-24 | View all the activity on an order (This should be developed in parallel to epics with priority 5-8)
OdysseyONE | LINX-5943 | Order Capability | LINX-7958 | Audit Trail | 4** | UI | Audit Trail for Manual & Integrated Orders (Multiple Line Items) - View Actions & Events | LINX-9128 |  |  |  | Complete | Yet to Start | 2026-04-20 | 2026-04-20 | View all the activity on an order (This should be developed in parallel to epics with priority 5-8)
OdysseyONE | LINX-5943 | Order Capability | LINX-7553 | Manual Order Creation (Quick Order) | 5 | UI | Quick Order Creation - General Information Section | LINX-8118 | 30 - 33 | 30 : 11-Mar-26 31 : 25-Mar-26 32 : 08-Apr-26 33 : 22-Apr-26 | 30 : 24-Mar-26 31 : 07-Apr-26 32 : 21-Apr-26 33 : 05-May-26 | Complete | Complete | 2026-04-09 | 2026-04-14 | Order Creation via UI (only mandatory fields)
OdysseyONE | LINX-5943 | Order Capability | LINX-7553 | Manual Order Creation (Quick Order) | 5 | UI | Quick Order Creation - Pickup / Delivery Section (Consignor and Consignee) | LINX-8119 |  |  |  | Complete | Complete | 2026-04-13 | 2026-04-14 | Order Creation via UI (only mandatory fields)
OdysseyONE | LINX-5943 | Order Capability | LINX-7553 | Manual Order Creation (Quick Order) | 5 | UI | Quick Order Creation - Ship and Delivery Date and Time (Consignor and Consignee) | LINX-8120 |  |  |  | Complete | Complete | 2026-04-13 | 2026-04-20 | Order Creation via UI (only mandatory fields)
OdysseyONE | LINX-5943 | Order Capability | LINX-7553 | Manual Order Creation (Quick Order) | 5 | UI | Quick Order Creation - Product Information Section (Add Product) | LINX-8121 |  |  |  | Complete | Yet to Start | WIP | Yet to start | Order Creation via UI (only mandatory fields)
OdysseyONE | LINX-5943 | Order Capability | LINX-7553 | Manual Order Creation (Quick Order) | 5 | UI | Quick Order Creation - Manage Column option for Product Information Section | LINX-8122 |  |  |  | WIP | Yet to Start | WIP | Yet to start | Order Creation via UI (only mandatory fields)
OdysseyONE | LINX-5943 | Order Capability | LINX-7553 | Manual Order Creation (Quick Order) | 5 | UI | Quick Order Creation - Reorder columns & change column width in Product Information section | LINX-8123 |  |  |  | WIP | Yet to Start | WIP | Yet to start | Order Creation via UI (only mandatory fields)
OdysseyONE | LINX-5943 | Order Capability | LINX-7553 | Manual Order Creation (Quick Order) | 5 | UI | Quick Order Creation - Special Services section (Manage Special Services) | LINX-8124 |  |  |  | Complete | Complete | 2026-04-13 | 2026-04-15 | Order Creation via UI (only mandatory fields)
OdysseyONE | LINX-5943 | Order Capability | LINX-7553 | Manual Order Creation (Quick Order) | 5 | UI | Quick Order Creation - Special Services section (Quick selection) | LINX-8125 |  |  |  | Complete | Complete | 2026-04-13 | 2026-04-15 | Order Creation via UI (only mandatory fields)
OdysseyONE | LINX-5943 | Order Capability | LINX-7553 | Manual Order Creation (Quick Order) | 5 | Backend | New Logic for fetching Special Services in Manual Orders (Quick Orders) | LINX-10985 |  |  |  | Complete | Yet to Start | TBD | TBD | Order Creation via UI (only mandatory fields)
OdysseyONE | LINX-5943 | Order Capability | LINX-7553 | Manual Order Creation (Quick Order) | 5 | UI | Quick Order Confirmation Page | LINX-9002 |  |  |  | Complete | Complete | 2026-04-13 | 2026-04-15 | Order Creation via UI (only mandatory fields)
OdysseyONE | LINX-5943 | Order Capability | LINX-7553 | Manual Order Creation (Quick Order) | 5 | UI | In-Order Actions in Quick Order Creation | LINX-9010 |  |  |  | Complete | Complete | 2026-04-13 | 2026-04-15 | Order Creation via UI (only mandatory fields)
OdysseyONE | LINX-5943 | Order Capability | LINX-7553 | Manual Order Creation (Quick Order) | 5 | Backend | QCA Routing Call from Order (Manual Order) | LINX-8100 |  |  |  | Completed (as a part of Phase 1 requirements) | Not Required | 2026-02-17 | 2026-02-24 | Requested on 13-Feb-26
OdysseyONE | LINX-5943 | Order Capability | LINX-7553 | Manual Order Creation (Quick Order) | 5 | Backend | QCP Rating Call from Order (Manual Order) | LINX-8101 |  |  |  | Complete | Not Required | 2026-02-17 | 2026-02-24 | Requested on 13-Feb-26
OdysseyONE | LINX-5943 | Order Capability | LINX-7553 | Manual Order Creation (Quick Order) | 5 | Backend | Search Functionality for Mandatory Fields in Manual Order Creation UI | LINX-9882 |  |  |  | Complete | Complete | 2026-05-20 | 2026-05-19 | Requested on 18-May-26
OdysseyONE | LINX-5943 | Order Capability | LINX-7556 | Manual Order - Edit, Cancel Order | 6 | UI | Order Overview / Summary Page - Post Order Creation Actions - Edit Order | LINX-10248 | 34, 35 | 34 - 06-May-26 35 - 20-May-26 | 34 - 19-May-26 35 - 02-Jun-26 | Complete | Yet to Start | 2026-05-26 | 2026-05-29 | Make changes to existing order (manual & integrated)
OdysseyONE | LINX-5943 | Order Capability | LINX-7556 | Manual Order - Edit, Cancel Order | 6 | UI | Order Overview / Summary Page - Post Order Creation Actions - Cancel Manual Order | LINX-10258 |  |  |  | Complete | Yet to Start | 2026-05-26 | 2026-05-29 | Cancel / Restore existing order
OdysseyONE | LINX-5943 | Order Capability | LINX-8026 | Manual Order Creation (Long Order) | 7 | UI | Long Order Creation - References Sub-Section (General Information Section) | LINX-8126 | 36-39 | 36 : 03-Jun-26 37 : 17-Jun-26 38 : 01-Jul-26 39 : 15-Jul-26 | 36 : 16-Jun-26 37 : 30-Jun-26 38 : 14-Jul-26 39 : 28-Jul-26 | Complete | Complete | 2026-04-09 | 2026-04-20 | Order Creation via UI (additional fields)
OdysseyONE | LINX-5943 | Order Capability | LINX-8026 | Manual Order Creation (Long Order) | 7 | UI | Long Order Creation - General section (Add Instructions) | LINX-8127 |  |  |  | Complete | Complete | 2026-04-09 | 2026-04-20 | Order Creation via UI (additional fields)
OdysseyONE | LINX-5943 | Order Capability | LINX-8026 | Manual Order Creation (Long Order) | 7 | UI | Long Order Creation - References section | LINX-8128 |  |  |  | Complete | Complete | 2026-04-20 | 2026-04-20 | Order Creation via UI (additional fields)
OdysseyONE | LINX-5943 | Order Capability | LINX-8026 | Manual Order Creation (Long Order) | 7 | UI | Long Order Creation - Pickup / Delivery section | LINX-8042 |  |  |  | Complete | Complete | 2026-04-20 | 2026-04-20 | Order Creation via UI (additional fields)
OdysseyONE | LINX-5943 | Order Capability | LINX-8026 | Manual Order Creation (Long Order) | 7 | UI | Long Order Creation - Ship and Delivery Date and Time (Consignor and Consignee) | LINX-8028 |  |  |  | Complete | Complete | 2026-04-20 | 2026-04-20 | Order Creation via UI (additional fields)
OdysseyONE | LINX-5943 | Order Capability | LINX-8026 | Manual Order Creation (Long Order) | 7 | UI | Long Order Creation - Product Information Section (Add Product - Product Details) | LINX-8131 |  |  |  | WIP | Yet to Start | WIP | Yet to start | Order Creation via UI (additional fields)
OdysseyONE | LINX-5943 | Order Capability | LINX-8026 | Manual Order Creation (Long Order) | 7 | UI | Long Order Creation - Product Information Section (Add Product - Add Reference Codes) | LINX-8132 |  |  |  | WIP | Yet to Start | WIP | Yet to start | Order Creation via UI (additional fields)
OdysseyONE | LINX-5943 | Order Capability | LINX-8026 | Manual Order Creation (Long Order) | 7 | UI | Long Order Creation - Product Information Section (Add Product - Add Hazmat) | LINX-8133 |  |  |  | WIP | Yet to Start | WIP | Yet to start | Order Creation via UI (additional fields)
OdysseyONE | LINX-5943 | Order Capability | LINX-8026 | Manual Order Creation (Long Order) | 7 | UI | Long Order Creation - Product Information Section (Add Product - General) | LINX-8134 |  |  |  | WIP | Yet to Start | WIP | Yet to start | Order Creation via UI (additional fields)
OdysseyONE | LINX-5943 | Order Capability | LINX-8026 | Manual Order Creation (Long Order) | 7 | UI | Long Order Creation - Product Information Section (Add Product - Packaging) | LINX-8135 |  |  |  | WIP | Yet to Start | WIP | Yet to start | Order Creation via UI (additional fields)
OdysseyONE | LINX-5943 | Order Capability | LINX-8026 | Manual Order Creation (Long Order) | 7 | UI | Long Order Creation - Special Services section (Manage Special Services) | LINX-8043 |  |  |  | Complete | Complete | 2026-04-20 | 2026-04-20 | Order Creation via UI (additional fields)
OdysseyONE | LINX-5943 | Order Capability | LINX-7553 | Manual Order Creation (Long Order) | 7 | Backend | New Logic for fetching Special Services in Manual Orders (Long Orders) | LINX-10986 |  |  |  | Complete | Yet to Start | TBD | TBD | Order Creation via UI (only mandatory fields)
OdysseyONE | LINX-5943 | Order Capability | LINX-8026 | Manual Order Creation (Long Order) | 7 | UI | Long Order Creation - Special Services section (Quick selection) | LINX-8044 |  |  |  | Complete | Complete | 2026-04-20 | 2026-04-20 | Order Creation via UI (additional fields)
OdysseyONE | LINX-5943 | Order Capability | LINX-8026 | Manual Order Creation (Long Order) | 7 | UI | Long Order Confirmation Summary Page | LINX-9004 |  |  |  | Complete | Complete | 2026-04-20 | 2026-04-20 | Order Creation via UI (additional fields)
OdysseyONE | LINX-5943 | Order Capability | LINX-8026 | Manual Order Creation (Long Order) | 7 | UI | In-Order Actions in Long Order Creation | LINX-9009 |  |  |  | Complete | Complete | 2026-04-20 | 2026-04-20 | Order Creation via UI (additional fields)
OdysseyONE | LINX-5943 | Order Capability | LINX-7554 | Order Copy | 8 | UI | Order Overview / Summary Page - Post Order Creation Actions - Copy Order | LINX-10259 | 40, 41 | 40 : 29-Jul-26 41 : 12-Aug-26 | 40 : 11-Aug-26 41 : 25-Aug-26 | Complete | Yet to Start | 2026-05-26 | 2026-06-01 | Copy all order fields from an existing order (apart from Order #, dates & carrier), to create a new order
OdysseyONE | LINX-5943 | Order Capability | LINX-7557 | Order overview & actions | 9 | UI | Order Management - Order Overview / Summary Page | LINX-9896 | 42-46 | 42 : 26-Aug-26 43 : 09-Sep-26 44 : 23-Sep-26 45 : 07-Oct-26 46 : 21-Oct-26 | 42 : 08-Sep-26 43 : 22-Sep-26 44 : 06-Oct-26 45 : 20-Oct-26 46 : 03-Nov-26 | Complete | Yet to Start | 2026-05-26 | 2026-05-29 | Single page snapshot of all orders
OdysseyONE | LINX-5943 | Order Capability | LINX-7557 | Order overview & actions | 9 | UI | Order Overview/Summary Page - Post Order Creation Actions & View Order | LINX-10233 |  |  |  | Complete | Yet to Start | 2026-05-26 | 2026-05-29 | View the contents of the order
OdysseyONE | LINX-5943 | Order Capability | LINX-7557 | Order overview & actions | 9 | UI | Order Management - Order Overview / Summary Page - Manage Columns | LINX-10300 |  |  |  | Complete | Yet to Start | 2026-05-26 | 2026-06-01 | Show/Hide Columns & Re-arrange columns
OdysseyONE | LINX-5943 | Order Capability | LINX-7557 | Order overview & actions | 9 | UI | Order Overview Page - Display Custom Views | LINX-10788 |  |  |  | Complete | Yet to Start | 2026-06-03 | Yet to start | Show existing custom views ( after show/hide , sequencing & applying filters)
OdysseyONE | LINX-5943 | Order Capability | LINX-7557 | Order overview & actions | 9 | UI | Order Overview Page - Create Custom Views | LINX-10814 |  |  |  | Complete | Yet to Start | 2026-06-03 | Yet to start | Create new custom views ( after show/hide , sequencing & applying filters)
OdysseyONE | LINX-5943 | Order Capability | LINX-7557 | Order overview & actions | 9 | UI | Order Overview Page - Edit Custom Views | LINX-10825 |  |  |  | Complete | Yet to Start | 2026-06-03 | Yet to start | Edit existing custom views ( after show/hide , sequencing & applying filters)
OdysseyONE | LINX-5943 | Order Capability | LINX-7557 | Order overview & actions | 9 | UI | Order Overview Page - Delete Custom Views | LINX-10838 |  |  |  | Complete | Yet to Start | 2026-06-03 | Yet to start | Delete existing custom views ( after show/hide , sequencing & applying filters)
OdysseyONE | LINX-5943 | Order Capability | LINX-7557 | Order overview & actions | 9 | UI | Order Management - Order Overview / Summary Page - View / Apply Filters | LINX-10285 |  |  |  | Complete | Yet to Start | 2026-05-26 | 2026-06-01 | Apply basic & advanced filters on the orders in the overview page
Note on J2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dependency - Master Data Integration is required