## Functional Req. Tracker
Jira Space | Master Epic # | Master Epic | Sub- Epic # | Sub-Epic | Sub-Epic Priority | Story Type (UI / Backend) | Type of Work Item | U/Story | U/Story # | Applicable for Oct Release? | Sprint No.(s) | Sprint Start Date | Sprint End Date | Requirements Gathering Status | Wireframes (Figma) Status | Story Readiness Status (Approval Date) | Grooming Status | Remarks
OdysseyONE |  |  | LINX-8681 | OdysseyOne Home Page (Internal Users) |  | UI | User Story | OdysseyONE Home Page - 'What would you like to do?' Widget - Go to Create a new Order | LINX-12876 | N | [6 empty] | Yet to Start | Home page for go lives needs navigation to all the production domains, only. Widgets can wait.. These stories all need business review and should be coordinated with the other Home Page stories for Shipment.
OdysseyONE |  |  | LINX-8681 | OdysseyOne Home Page (Internal Users) |  | UI | User Story | OdysseyONE Home Page - Orders with Data Validation Errors (Widget 1) | LINX-13024 | N | [6 empty] | Yet to Start
OdysseyONE |  |  | LINX-8681 | OdysseyOne Home Page (Internal Users) |  | UI | User Story | OdysseyONE Home Page - Orders in Draft Status (Widget 2) | LINX-13066 | N | [6 empty] | Yet to Start
OdysseyONE |  |  | LINX-8681 | OdysseyOne Home Page (Internal Users) |  | UI | User Story | OdysseyONE Home Page - Orders in Cancelled Status (Widget 3) | LINX-13070 | N | [6 empty] | Yet to Start
OdysseyONE |  |  | LINX-8681 | OdysseyOne Home Page (Internal Users) |  | UI | User Story | OdysseyONE Home Page - Tracking / Reporting Metrics (Widget 4) | LINX-13073 | N
OdysseyONE | LINX-5943 | Order Capability | LINX-7552 | Integrated Order Creation & Validation | 1 | Backend | User Story | Data Mapping for Integrated Orders | LINX-8063 | Y | 28, 29, 33 | 28 : 11-Feb-26 29 : 25-Feb-26 33 : 22-Apr-26 | 28 : 24-Feb-26 29 : 10-Mar-26 33 : 05-May-26 | Complete | Not Required | 2026-02-09 | 2026-02-09 | Same validations as Phase 1. Orders from the legacy TMS are already validated unlike orders from LINX
OdysseyONE | LINX-5943 | Order Capability | LINX-7552 | Integrated Order Creation & Validation | 1 | Backend | User Story | Validations for Integrated Orders - Mandatory fields | LINX-8064 | Y | 28, 29, 33 | 28 : 11-Feb-26 29 : 25-Feb-26 33 : 22-Apr-26 | 28 : 24-Feb-26 29 : 10-Mar-26 33 : 05-May-26 | Complete | Not Required | 2026-02-09 | 2026-02-09 | Same validations as Phase 1. Orders from the legacy TMS are already validated unlike orders from LINX
OdysseyONE | LINX-5943 | Order Capability | LINX-7552 | Integrated Order Creation & Validation | 1 | Backend | User Story | Validations for Integrated Orders - Conditional fields | LINX-8066 | Y | 28, 29, 33 | 28 : 11-Feb-26 29 : 25-Feb-26 33 : 22-Apr-26 | 28 : 24-Feb-26 29 : 10-Mar-26 33 : 05-May-26 | Complete | Not Required | 2026-02-09 | 2026-02-09 | Same validations as Phase 1. Orders from the legacy TMS are already validated unlike orders from LINX
OdysseyONE | LINX-5943 | Order Capability | LINX-7552 | Integrated Order Creation & Validation | 1 | Backend | User Story | Validations for Integrated Orders - Additional fields | LINX-8067 | Y | 28, 29, 33 | 28 : 11-Feb-26 29 : 25-Feb-26 33 : 22-Apr-26 | 28 : 24-Feb-26 29 : 10-Mar-26 33 : 05-May-26 | Complete | Not Required | 2026-02-09 | 2026-02-09 | Same validations as Phase 1. Orders from the legacy TMS are already validated unlike orders from LINX
OdysseyONE | LINX-5943 | Order Capability | LINX-7552 | Integrated Order Creation & Validation | 1 | UI | User Story | OIF UI to fix validation errors for integrated orders | LINX-11137 | Y | 28, 29, 33 | 28 : 11-Feb-26 29 : 25-Feb-26 33 : 22-Apr-26 | 28 : 24-Feb-26 29 : 10-Mar-26 33 : 05-May-26 | Complete | 2026-07-23 | 2026-06-15 | 2026-06-19
OdysseyONE | LINX-5943 | Order Capability | LINX-7552 | Integrated Order Creation & Validation | 1 | Backend | User Story | Country, Region, City and Postal Code - Validation for Integrated Orders | LINX-8068 | Y | 28, 29, 33 | 28 : 11-Feb-26 29 : 25-Feb-26 33 : 22-Apr-26 | 28 : 24-Feb-26 29 : 10-Mar-26 33 : 05-May-26 | Complete | Not Required | 2026-02-09 | 2026-02-10 | Same validations as Phase 1. Orders from the legacy TMS are already validated unlike orders from LINX
OdysseyONE | LINX-5943 | Order Capability | LINX-7552 | Integrated Order Creation & Validation | 1 | Backend | User Story | QCA Routing Call from Order (Integrated Order) | LINX-9021 | Y | 28, 29, 33 | 28 : 11-Feb-26 29 : 25-Feb-26 33 : 22-Apr-26 | 28 : 24-Feb-26 29 : 10-Mar-26 33 : 05-May-26 | Complete | Not Required | 2026-04-10 | 24-Feb-26 (Earlier story applies) | Requested on 10-Apr-26 to create separate stories for Manual & Integ Orders
OdysseyONE | LINX-5943 | Order Capability | LINX-7552 | Integrated Order Creation & Validation | 1 | Backend | User Story | QCP Rating Call from Order (Integrated Order) | LINX-9020 | Y | 28, 29, 33 | 28 : 11-Feb-26 29 : 25-Feb-26 33 : 22-Apr-26 | 28 : 24-Feb-26 29 : 10-Mar-26 33 : 05-May-26 | Complete | Not Required | 2026-04-10 | 24-Feb-26 (Earlier story applies) | Requested on 10-Apr-26 to create separate stories for Manual & Integ Orders
|  | Order Capability | LINX-7552 | Integrated Order Creation & Validation | 1 | Backend | User Story | Additional Mapping & Validation Clarification for OrderIn XML | LINX-9247 | Y |  |  |  | Complete | Not Required | 2026-04-10 | N/A - Feedback from the Dave
OdysseyONE | LINX-5943 | Order Capability | LINX-7552 | Integrated Order Creation & Validation | 1 | Backend | User Story | Integrated Order - Cancelling a non-existent order - Rephrase Error Message | LINX-10683 | Y | 28, 29, 33 | 28 : 11-Feb-26 29 : 25-Feb-26 33 : 22-Apr-26 | 28 : 24-Feb-26 29 : 10-Mar-26 33 : 05-May-26 | Complete | Not Required | 2026-05-29 | N/A - Feedback from the Demo | Feedback from Demo on 28-May-26
OdysseyONE | LINX-5943 | Order Capability | LINX-7552 | Integrated Order Creation & Validation | 1 | Backend | Task | Address, Time & Time-Zone Validation (Sprint-End Demo Feedback) | LINX-13548 | Y |  |  |  | Complete | Not Required | 2026-07-17 | N/A - Feedback from the Demo | Feedback from Demo on 16-Jul-26
OdysseyONE | LINX-5943 | Order Capability | LINX-7558 | Master Data Integration | 2 | Backend | User Story | Master Data for Order Creation | LINX-8062 | Y | 28 - 30 | 28 : 11-Feb-26 29 : 25-Feb-26 30 : 11-Mar-26 | 28 : 24-Feb-26 29 : 10-Mar-26 30 : 24-Mar-26 | Complete | Not Required | 2026-02-09 | 2026-02-10 | Same validations as Phase 1. Orders from the legacy TMS are already validated unlike orders from LINX
OdysseyONE | LINX-5943 | Order Capability | LINX-7555 | Order Lifecycle Management | 3 | Backend | User Story | Order Lifecycle for Integrated Orders | LINX-6001 | Y | 31-33 | 31 : 25-Mar-26 32 : 08-Apr-26 33 : 22-Apr-26 | 31 : 07-Apr-26 32 : 21-Apr-26 33 : 05-May-26 | Complete | Not Required | 2026-01-29 | 2-Feb-26 | Order Statuses for orders from customer ERP
OdysseyONE | LINX-5943 | Order Capability | LINX-7555 | Order Lifecycle Management | 3 | Backend | User Story | Order Lifecycle for Manual Orders | LINX-6081 | Y | 31-33 | 31 : 25-Mar-26 32 : 08-Apr-26 33 : 22-Apr-26 | 31 : 07-Apr-26 32 : 21-Apr-26 33 : 05-May-26 | Complete | Not Required | 2026-01-29 | 2-Feb-26 | Order Statuses for orders from UI
OdysseyONE | LINX-5943 | Order Capability | LINX-7555 | Order Lifecycle Management | 3 | Backend | User Story | Order Lifecycle during Order Editing (Manual & Integrated Orders) | LINX-11185 | Y |  |  |  | Complete | Not Required | 2026-06-18 | 2026-06-19
OdysseyONE | LINX-5943 | Order Capability | LINX-7958 | Audit Trail | 4** | UI | User Story | Audit Trail for Manual & Integrated Orders (Single Line Item) - View Actions & Events | LINX-8091 | Y |  |  |  | Complete | Not Yet Available | 2026-02-18 | 2026-02-24 | View all the activity on an order (This should be developed in parallel to epics with priority 5-8)
OdysseyONE | LINX-5943 | Order Capability | LINX-7958 | Audit Trail | 4** | UI | User Story | Audit Trail for Manual & Integrated Orders (Multiple Line Items) - View Actions & Events | LINX-9128 | Y |  |  |  | Complete | Not Yet Available | 2026-04-20 | 2026-04-20 | View all the activity on an order (This should be developed in parallel to epics with priority 5-8)
OdysseyONE | LINX-5943 | Order Capability | LINX-7553 | Manual Order Creation (Quick Order) | 5 | UI | User Story | Quick Order Creation - General Information Section | LINX-8118 | Y | 30 - 33 | 30 : 11-Mar-26 31 : 25-Mar-26 32 : 08-Apr-26 33 : 22-Apr-26 | 30 : 24-Mar-26 31 : 07-Apr-26 32 : 21-Apr-26 33 : 05-May-26 | Complete | Complete | 2026-04-09 | 2026-04-14 | Order Creation via UI (only mandatory fields)
OdysseyONE | LINX-5943 | Order Capability | LINX-7553 | Manual Order Creation (Quick Order) | 5 | UI | Task | Renaming 'Owning Organization' to 'Customer' (Feedback from Lauren) | LINX-13553 | Y |  |  |  | Complete | Complete | 2026-07-16 | N/A - Feedback from Lauren | Feedback from Lauren
OdysseyONE | LINX-5943 | Order Capability | LINX-7553 | Manual Order Creation (Quick Order) | 5 | UI | User Story | Quick Order Creation - General Information Section - 'Hazardous' Flag for Order | LINX-12102 | Y |  |  |  | Complete | Not Yet Available -New Req | 2026-06-25 | 2026-06-29 | Hazardous flag for the order. If atleast one order line item is hazardous, the entire order is considered hazardous
OdysseyONE | LINX-5943 | Order Capability | LINX-7553 | Manual Order Creation (Quick Order) | 5 | UI | User Story | Quick Order Creation - Pickup / Delivery Section (Consignor and Consignee) | LINX-8119 | Y |  |  |  | Complete | Complete | 2026-04-13 | 2026-04-14 | Order Creation via UI (only mandatory fields)
OdysseyONE | LINX-5943 | Order Capability | LINX-7553 | Manual Order Creation (Quick Order) | 5 | UI | User Story | Quick Order Creation - Ship and Delivery Date and Time (Consignor and Consignee) | LINX-8120 | Y |  |  |  | Complete | Complete | 2026-04-13 | 2026-04-20 | Order Creation via UI (only mandatory fields)
OdysseyONE | LINX-5943 | Order Capability | LINX-7553 | Manual Order Creation (Quick Order) | 5 | UI | User Story | Quick Order Creation - Ship and Delivery Date and Time - 'Appointment' Flag for Order | LINX-12095 | Y |  |  |  | Complete | 2026-07-25 | 2026-06-25 | 2026-06-29 | Add a checkbox titled 'Appointment' - 1 each in Pickup & Delivery section. Clicking on the box means the order HAS TO BE COMPULSORILY picked up/dropped at the date/time . Requested on 24-Jun-26
OdysseyONE | LINX-5943 | Order Capability | LINX-7553 | Manual Order Creation (Quick Order) | 5 | UI | User Story | Quick Order Creation - Product Information Section (Add Product) | LINX-8121 | Y |  |  |  | Complete | 2026-07-23 | 2026-06-17 | 2026-06-19 | Depends on Equipment selected - LINX-13893
OdysseyONE | LINX-5943 | Order Capability | LINX-7553 | Manual Order Creation (Quick Order) | 5 | UI | User Story | Quick Order Creation - Manage Column option for Product Information Section | LINX-8122 | N |  |  |  | Complete | Not Yet Available - Use Ref UI | 2026-06-18 | 2026-06-19 | Order Creation via UI (only mandatory fields)
OdysseyONE | LINX-5943 | Order Capability | LINX-7553 | Manual Order Creation (Quick Order) | 5 | UI | User Story | Quick Order Creation - Reorder columns & change column width in Product Information section | LINX-8123 | N |  |  |  | Complete | Not Yet Available - Use Ref UI | 2026-06-18 | 2026-06-19 | Order Creation via UI (only mandatory fields)
OdysseyONE | LINX-5943 | Order Capability | LINX-7553 | Manual Order Creation (Quick Order) | 5 | UI | User Story | Quick Order Creation - Special Services section (Manage Special Services) | LINX-8124 | Y |  |  |  | Complete | Complete | 2026-04-13 | 2026-04-15 | Order Creation via UI (only mandatory fields)
OdysseyONE | LINX-5943 | Order Capability | LINX-7553 | Manual Order Creation (Quick Order) | 5 | UI | User Story | Quick Order Creation - Special Services section (Quick selection) | LINX-8125 | Y |  |  |  | Complete | Complete | 2026-04-13 | 2026-04-15 | Order Creation via UI (only mandatory fields)
OdysseyONE / Managed Service TMS | LINX-5943 / MST-389 | Order Capability | LINX-7553 | Manual Order Creation (Quick Order) | 5 | Backend | User Story | New Logic for fetching Special Services in Manual (Quick & Long) Orders (Short Term Strategy) | LINX-10985 | Y |  |  |  | Complete | Not Required | 2026-06-18 | 2026-06-19 | Order Creation via UI (only mandatory fields). David requested to move to MST Jira Board & assign to Doug Albritton
OdysseyONE | LINX-5943 | Order Capability | LINX-7553 | Manual Order Creation (Quick Order) | 5 | UI | User Story | Quick Order Confirmation Page | LINX-9002 | Y |  |  |  | Complete | Complete | 2026-04-13 | 2026-04-15 | Order Creation via UI (only mandatory fields)
OdysseyONE | LINX-5943 | Order Capability | LINX-7553 | Manual Order Creation (Quick Order) | 5 | UI | User Story | In-Order Actions in Quick Order Creation (Save/Save for Later/Discard) | LINX-9010 | Y |  |  |  | Complete | Complete | 2026-04-13 | 2026-04-15 | Order Creation via UI (only mandatory fields)
OdysseyONE | LINX-5943 | Order Capability | LINX-7553 | Manual Order Creation (Quick Order) | 5 | Backend | User Story | QCA Routing Call from Order (Manual Order) | LINX-8100 | Y |  |  |  | Completed (as a part of Phase 1 requirements) | Not Required | 2026-02-17 | 2026-02-24 | Requested on 13-Feb-26
OdysseyONE | LINX-5943 | Order Capability | LINX-7553 | Manual Order Creation (Quick Order) | 5 | Backend | User Story | QCP Rating Call from Order (Manual Order) | LINX-8101 | Y |  |  |  | Complete | Not Required | 2026-02-17 | 2026-02-24 | Requested on 13-Feb-26
OdysseyONE | LINX-5943 | Order Capability | LINX-7553 | Manual Order Creation (Quick Order) | 5 | Backend | User Story | Search Logic for Mandatory Fields in Manual Order Creation UI | LINX-9882 | N |  |  |  | Complete | Not Required | 2026-05-20 | 2026-05-19 | Requested on 18-May-26
OdysseyONE | LINX-5943 | Order Capability | LINX-7553 | Manual Order Creation (Quick Order) | 5 | UI | Task | Renaming 'Consignor' to 'Shipper' in the Pickup/Delivery Section | LINX-12255 | Y |  |  |  | Complete | Not Yet Available - Use Ref UI |  | N/A - Feedback from Demo
|  |  |  | Manual Order Creation (Quick Order) | 5 | UI | Task | Renaming 'Consignee' to 'Destination' in the Pickup/Delivery Section (David's Feedback) | LINX-13899 | Y |  |  |  | Complete |  |  | N/A - Feedback from Dave
OdysseyONE | LINX-5943 | Order Capability | LINX-7553 | Manual Order Creation (Quick Order) | 5 | UI | Task | Renaming Main Banner for Manual Order UI | LINX-12257 | Y |  |  |  | Complete | Not Yet Available - Use Ref UI |  | N/A - Feedback from Demo
OdysseyONE | LINX-5943 | Order Capability | LINX-7553 | Manual Order Creation (Quick Order) | 5 | UI | Task | Remove sub-text from all Quick Order sections (Feedback from Lauren) | LINX-13563 | Y |  |  |  | Complete | Complete | 2026-07-17 | N/A - Feedback from Lauren | Feedback from Lauren
OdysseyONE | LINX-5943 | Order Capability | LINX-7553 | Manual Order Creation (Quick Order) | 5 | UI | Task | "Appointment' Flag application in other Order functionalities | LINX-13869 | Y |  |  |  | Complete | Complete | 2026-07-23
OdysseyONE | LINX-5943 | Order Capability | LINX-7553 | Manual Order Creation (Quick Order) | 5 | UI | Task | Product Information' section field applicability based on selected 'Equipment' (Quick Order) - Lauren's Feedback | LINX-13893 | Y |  |  |  | Complete | 2026-07-23 | 2026-07-23 | N/A - Feedback from Lauren
OdysseyONE | LINX-5943 | Order Capability | LINX-7556 | Manual Order - Edit, Cancel Order | 6 | UI | User Story | Order Overview / Summary Page - Post Order Creation Actions - Edit Order | LINX-10248 | Y | 34, 35 | 34 - 06-May-26 35 - 20-May-26 | 34 - 19-May-26 35 - 02-Jun-26 | Complete | Not Yet Available | 2026-05-26 | 2026-05-29 | Make changes to existing order (manual & integrated)
OdysseyONE | LINX-5943 | Order Capability | LINX-7556 | Manual Order - Edit, Cancel Order | 6 | UI | User Story | Order Overview / Summary Page - Post Order Creation Actions - Cancel Manual Order | LINX-10258 | Y | 34, 35 | 34 - 06-May-26 35 - 20-May-26 | 34 - 19-May-26 35 - 02-Jun-26 | Complete | Not Yet Available | 2026-05-26 | 2026-05-29 | Cancel existing order
OdysseyONE | LINX-5943 | Order Capability | LINX-7556 | Manual Order - Edit, Cancel Order | 6 | UI | User Story | Order Overview / Summary Page - Post Order Creation Actions - Restore Manual Order | LINX-12309 | N |  |  |  | Complete | Not Yet Available | 2026-05-26 | 2026-05-29 | Restore existing order
OdysseyONE | LINX-5943 | Order Capability | LINX-8026 | Manual Order Creation (Long Order) | 7 | UI | User Story | Long Order Creation - References Sub-Section (General Information Section) | LINX-8126 | N | 36-39 | 36 : 03-Jun-26 37 : 17-Jun-26 38 : 01-Jul-26 39 : 15-Jul-26 | 36 : 16-Jun-26 37 : 30-Jun-26 38 : 14-Jul-26 39 : 28-Jul-26 | Complete | Complete | 2026-04-09 | 2026-04-20 | Order Creation via UI (additional fields)
OdysseyONE | LINX-5943 | Order Capability | LINX-8026 | Manual Order Creation (Long Order) | 7 | UI | User Story | Long Order Creation - General section (Add Instructions) | LINX-8127 | N | 36-39 | 36 : 03-Jun-26 37 : 17-Jun-26 38 : 01-Jul-26 39 : 15-Jul-26 | 36 : 16-Jun-26 37 : 30-Jun-26 38 : 14-Jul-26 39 : 28-Jul-26 | Complete | Complete | 2026-04-09 | 2026-04-20 | Order Creation via UI (additional fields)
OdysseyONE | LINX-5943 | Order Capability | LINX-8026 | Manual Order Creation (Long Order) | 7 | UI | User Story | Long Order Creation - References section | LINX-8128 | N | 36-39 | 36 : 03-Jun-26 37 : 17-Jun-26 38 : 01-Jul-26 39 : 15-Jul-26 | 36 : 16-Jun-26 37 : 30-Jun-26 38 : 14-Jul-26 39 : 28-Jul-26 | Complete | Complete | 2026-04-20 | 2026-04-20 | Order Creation via UI (additional fields)
OdysseyONE | LINX-5943 | Order Capability | LINX-8026 | Manual Order Creation (Long Order) | 7 | UI | User Story | Long Order Creation - Pickup / Delivery section | LINX-8042 | N | 36-39 | 36 : 03-Jun-26 37 : 17-Jun-26 38 : 01-Jul-26 39 : 15-Jul-26 | 36 : 16-Jun-26 37 : 30-Jun-26 38 : 14-Jul-26 39 : 28-Jul-26 | Complete | Complete | 2026-04-20 | 2026-04-20 | Order Creation via UI (additional fields)
OdysseyONE | LINX-5943 | Order Capability | LINX-8026 | Manual Order Creation (Long Order) | 7 | UI | Task | Auto-Population of Address fields based on Org ID & Long Name (Sprint-End Demo Feedback) | LINX-13549 | N |  |  |  | Complete | Complete | 2026-07-17 | N/A - Feedback from Demo | Feedback from Demo on 16-Jul-26
OdysseyONE | LINX-5943 | Order Capability | LINX-8026 | Manual Order Creation (Long Order) | 7 | UI | User Story | Long Order Creation - Ship and Delivery Date and Time (Consignor and Consignee) | LINX-8028 | N | 36-39 | 36 : 03-Jun-26 37 : 17-Jun-26 38 : 01-Jul-26 39 : 15-Jul-26 | 36 : 16-Jun-26 37 : 30-Jun-26 38 : 14-Jul-26 39 : 28-Jul-26 | Complete | Complete | 2026-04-20 | 2026-04-20 | Order Creation via UI (additional fields)
OdysseyONE | LINX-5943 | Order Capability | LINX-8026 | Manual Order Creation (Long Order) | 7 | UI | User Story | Long Order Creation - Product Information Section (Add Product - General) | LINX-8134 | N | 36-39 | 36 : 03-Jun-26 37 : 17-Jun-26 38 : 01-Jul-26 39 : 15-Jul-26 | 36 : 16-Jun-26 37 : 30-Jun-26 38 : 14-Jul-26 39 : 28-Jul-26 | Complete | Not Yet Available - Use Ref UI | 2026-06-18 | 2026-06-22 | Same fields as Phase 1. Only a UI refresh is required
OdysseyONE | LINX-5943 | Order Capability | LINX-8026 | Manual Order Creation (Long Order) | 7 | UI | User Story | Long Order Creation - Product Information Section (Add Product - Packaging) | LINX-8135 | N | 36-39 | 36 : 03-Jun-26 37 : 17-Jun-26 38 : 01-Jul-26 39 : 15-Jul-26 | 36 : 16-Jun-26 37 : 30-Jun-26 38 : 14-Jul-26 39 : 28-Jul-26 | Complete | Not Yet Available - Use Ref UI | 2026-06-18 | 2026-06-22 | Same fields as Phase 1. Only a UI refresh is required
OdysseyONE | LINX-5943 | Order Capability | LINX-8026 | Manual Order Creation (Long Order) | 7 | UI | User Story | Long Order Creation - Product Information Section (Add Product - Product Details) | LINX-8131 | N | 36-39 | 36 : 03-Jun-26 37 : 17-Jun-26 38 : 01-Jul-26 39 : 15-Jul-26 | 36 : 16-Jun-26 37 : 30-Jun-26 38 : 14-Jul-26 39 : 28-Jul-26 | Complete | Not Yet Available - Use Ref UI | 2026-06-18 | 2026-06-22 | Same fields as Phase 1. Only a UI refresh is required
OdysseyONE | LINX-5943 | Order Capability | LINX-8026 | Manual Order Creation (Long Order) | 7 | UI | User Story | Long Order Creation - Product Information Section (Add Product - Add Hazmat) | LINX-8133 | N | 36-39 | 36 : 03-Jun-26 37 : 17-Jun-26 38 : 01-Jul-26 39 : 15-Jul-26 | 36 : 16-Jun-26 37 : 30-Jun-26 38 : 14-Jul-26 39 : 28-Jul-26 | Complete | Not Yet Available - Use Ref UI | 2026-06-18 | 2026-06-22 | Same fields as Phase 1. Only a UI refresh is required
OdysseyONE | LINX-5943 | Order Capability | LINX-8026 | Manual Order Creation (Long Order) | 7 | UI | User Story | Long Order Creation - Product Information Section (Add Product - Add Reference Codes) | LINX-8132 | N | 36-39 | 36 : 03-Jun-26 37 : 17-Jun-26 38 : 01-Jul-26 39 : 15-Jul-26 | 36 : 16-Jun-26 37 : 30-Jun-26 38 : 14-Jul-26 39 : 28-Jul-26 | Complete | Not Yet Available - Use Ref UI | 2026-06-18 | 2026-06-22 | Same fields as Phase 1. Only a UI refresh is required
OdysseyONE | LINX-5943 | Order Capability | LINX-8026 | Manual Order Creation (Long Order) | 7 | UI | User Story | Long Order Creation - Product Information Section (Add Product - Product / Line Level Instructions) | LINX-11985 | N |  |  |  | Complete | Not Yet Available | Awaiting Approval | Yet to Start | Steve has asked to wait.
OdysseyONE | LINX-5943 | Order Capability | LINX-8026 | Manual Order Creation (Long Order) | 7 | UI | User Story | Long Order Creation - Special Services section (Manage Special Services) | LINX-8043 | N | 36-39 | 36 : 03-Jun-26 37 : 17-Jun-26 38 : 01-Jul-26 39 : 15-Jul-26 | 36 : 16-Jun-26 37 : 30-Jun-26 38 : 14-Jul-26 39 : 28-Jul-26 | Complete | Complete | 2026-04-20 | 2026-04-20 | Order Creation via UI (additional fields)
OdysseyONE / Managed Service TMS | LINX-5943 / MST-390 | Order Capability | LINX-7553 | Manual Order Creation (Long Order) | 7 | Backend | User Story | New Logic for fetching Special Services in Manual (Quick & Long) Orders (Long Term Strategy) | LINX-10986 | N | 36-39 | 36 : 03-Jun-26 37 : 17-Jun-26 38 : 01-Jul-26 39 : 15-Jul-26 | 36 : 16-Jun-26 37 : 30-Jun-26 38 : 14-Jul-26 39 : 28-Jul-26 | Complete | Not Required | 2026-06-18 | 2026-06-19 | Order Creation via UI (only mandatory fields).David requested to move to MST Jira Board & assign to Doug Albritton
OdysseyONE | LINX-5943 | Order Capability | LINX-8026 | Manual Order Creation (Long Order) | 7 | UI | User Story | Long Order Creation - Special Services section (Quick selection) | LINX-8044 | N | 36-39 | 36 : 03-Jun-26 37 : 17-Jun-26 38 : 01-Jul-26 39 : 15-Jul-26 | 36 : 16-Jun-26 37 : 30-Jun-26 38 : 14-Jul-26 39 : 28-Jul-26 | Complete | Complete | 2026-04-20 | 2026-04-20 | Order Creation via UI (additional fields)
OdysseyONE | LINX-5943 | Order Capability | LINX-8026 | Manual Order Creation (Long Order) | 7 | UI | User Story | Long Order Confirmation Summary Page | LINX-9004 | N |  |  |  | Complete | Complete | 2026-04-20 | 2026-04-20 | Order Creation via UI (additional fields)
OdysseyONE | LINX-5943 | Order Capability | LINX-8026 | Manual Order Creation (Long Order) | 7 | UI | User Story | In-Order Actions in Long Order Creation | LINX-9009 | N |  |  |  | Complete | Complete | 2026-04-20 | 2026-04-20 | Order Creation via UI (additional fields)
|  | Order Capability | LINX-8026 | Manual Order Creation (Long Order) | 7 | UI | Task | Change in field types for 'Reference Type' & 'Reference Value' (Lauren's Feedback) | LINX-13833 | N |  |  |  | Complete | Complete | 2026-07-22 | N/A - Feedback from Lauren | Feedback from Lauren
OdysseyONE | LINX-5943 | Order Capability | LINX-7554 | Order Copy | 8 | UI | User Story | Order Overview / Summary Page - Post Order Creation Actions - Copy Order | LINX-10259 | N | 40, 41 | 40 : 29-Jul-26 41 : 12-Aug-26 | 40 : 11-Aug-26 41 : 25-Aug-26 | Complete | Not Yet Available | 2026-05-26 | 2026-06-01 | Copy all order fields from an existing order (apart from Order #, dates & carrier), to create a new order
OdysseyONE | LINX-5943 | Order Capability | LINX-7557 | Order overview & actions | 9 | UI | User Story | Order Management - Order Overview / Summary Page | LINX-9896 | Y | 42-46 | 42 : 26-Aug-26 43 : 09-Sep-26 44 : 23-Sep-26 45 : 07-Oct-26 46 : 21-Oct-26 | 42 : 08-Sep-26 43 : 22-Sep-26 44 : 06-Oct-26 45 : 20-Oct-26 46 : 03-Nov-26 | Complete | 2026-07-23 | 2026-05-26 | 2026-05-29 | Single page snapshot of all orders
OdysseyONE | LINX-5943 | Order Capability | LINX-7557 | Order overview & actions | 9 | UI | User Story | Order Management - Order Overview/Summary Page - 'All' Tab | LINX-11658 | Y |  |  |  | Complete | 2026-07-23 | 2026-06-18 | 2026-06-29
OdysseyONE | LINX-5943 | Order Capability | LINX-7557 | Order overview & actions | 9 | UI | User Story | Order Management - Order Overview / Summary Page - 'Validation Errors' Tab | LINX-11659 | Y |  |  |  | Complete | 2026-07-23 | Awaiting Approval | 29-06-2026 (Overview provided since UI is not available) | UI to display overview of integrated orders having validation errors
OdysseyONE | LINX-5943 | Order Capability | LINX-7557 | Order overview & actions | 9 | UI | User Story | Order Management - Order Overview / Summary Page - 'Draft' Tab | LINX-11663 | Y |  |  |  | Complete | 2026-07-23 | Awaiting Approval | 29-06-2026 (Overview provided since UI is not available) | UI to display overview of orders in 'Draft' Status (currently being edited & not submitted OR during manual order creation, user clicked on 'Save' or 'Save for Later' )
OdysseyONE | LINX-5943 | Order Capability | LINX-7557 | Order overview & actions | 9 | UI | User Story | Order Overview/Summary Page - Post Order Creation Actions & View Order | LINX-10233 | Y |  |  |  | Complete | Not Yet Available | 2026-05-26 | 2026-05-29 | View the contents of the order
OdysseyONE | LINX-5943 | Order Capability | LINX-7557 | Order overview & actions | 9 | UI | User Story | Order Management - Order Overview / Summary Page - Manage Columns (ON HOLD) | LINX-10300 | N |  |  |  | Complete | Not Yet Available | 2026-05-26 | 2026-06-01 | Show/Hide Columns & Re-arrange columns. ON HOLD since it requires integration with user management
OdysseyONE | LINX-5943 | Order Capability | LINX-7557 | Order overview & actions | 9 | UI | User Story | Order Overview Page - Display Custom Views (ON HOLD) | LINX-10788 | N |  |  |  | Complete | Not Yet Available | Awaiting Approval | Yet to start | Show existing custom views ( after show/hide , sequencing & applying filters). ON HOLD since it requires integration with user management
OdysseyONE | LINX-5943 | Order Capability | LINX-7557 | Order overview & actions | 9 | UI | User Story | Order Overview Page - Create Custom Views (ON HOLD) | LINX-10814 | N |  |  |  | Complete | Not Yet Available | Awaiting Approval | Yet to start | Create new custom views ( after show/hide , sequencing & applying filters). ON HOLD since it requires integration with user management
OdysseyONE | LINX-5943 | Order Capability | LINX-7557 | Order overview & actions | 9 | UI | User Story | Order Overview Page - Edit Custom Views (ON HOLD) | LINX-10825 | N |  |  |  | Complete | Not Yet Available | Awaiting Approval | Yet to start | Edit existing custom views ( after show/hide , sequencing & applying filters). ON HOLD since it requires integration with user management
OdysseyONE | LINX-5943 | Order Capability | LINX-7557 | Order overview & actions | 9 | UI | User Story | Order Overview Page - Delete Custom Views (ON HOLD) | LINX-10838 | N |  |  |  | Complete | Not Yet Available | Awaiting Approval | Yet to start | Delete existing custom views ( after show/hide , sequencing & applying filters). ON HOLD since it requires integration with user management
OdysseyONE | LINX-5943 | Order Capability | LINX-7557 | Order overview & actions | 9 | UI | User Story | Order Management - Order Overview / Summary Page - View / Apply Basic Filters | LINX-10285 | Y |  |  |  | Complete | Not Yet Available | 2026-05-26 | 2026-06-01 | Apply basic filters on the orders in the overview page. Requested by Saikat on 19-Jun to split basic & advanced filters into separate stories
OdysseyONE | LINX-5943 | Order Capability | LINX-7557 | Order overview & actions | 9 | UI | User Story | Order Management - Order Overview / Summary Page - View / Apply Advanced Filters | LINX-11895 | N |  |  |  | Complete | Not Yet Available | 2026-05-26 | 2026-06-01 | Apply advanced filters on the orders in the overview page
Note on L7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dependency - Master Data Integration is required
Note on L8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dependency - Master Data Integration is required
Note on L9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dependency - Master Data Integration is required
Note on L10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dependency - Master Data Integration is required
Note on L11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dependency - Master Data Integration is required
Note on L12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dependency - Master Data Integration is required
Note on L13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dependency - Master Data Integration is required
Note on L14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dependency - Master Data Integration is required
Note on L16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dependency - Master Data Integration is required

## Sheet1 (hidden)
U/Story | U/Story #
Renaming 'Consignor' to 'Shipper' in the Pickup/Delivery Section (Task) | LINX-12255 | LINX-8119
Renaming Main Banner for Manual Order UI (Task) | LINX-12257 | LINX-7553
Address, Time & Time-Zone Validation (Sprint-End Demo Feedback) - Task | LINX-13548 | LINX-8042
Auto-Population of Address fields based on Org ID & Long Name (Sprint-End Demo Feedback) | LINX-13549 | LINX-8042
Renaming 'Owning Organization' to 'Customer' (Feedback from Lauren) | LINX-13553 | LINX-8118
Remove sub-text from all Quick Order sections (Feedback from Lauren) - Task | LINX-13563 | LINX-7553
Change in field types for 'Reference Type' & 'Reference Value' (Lauren's Feedback) - Task | LINX-13833 | LINX-8128
Appointment' Flag application in other Order functionalities (Task) | LINX-13869 | LINX-7553
Product Information' section field applicability based on selected 'Equipment' (Quick Order) - Lauren's Feedback (Task) | LINX-13893 | LINX-8121
Renaming 'Consignee' to 'Destination' in the Pickup/Delivery Section (David's Feedback) - Task | LINX-13899 | LINX-8119